## SCOPE
FY20 Coastal Resilience Grant - Evaluation of Coastal Processes and Storm Impacts to Support Resilient Planning and Mitigation Strategies for the Vineyard Haven Harbor Shoreline
Project Task Description | Deliverables | Deliverable Due Date | Invoice Due Date | Grant | Match | Total
Task 1: Site -Specific Analysis of Overtopping and Coastal Flooding
Sub-task 1.1 - Kick-Off Meeting | Sign In Sheet and Meeting Notes | 2019-10-15 | 2019-11-15 | 2964 | 970 | 3934
Sub-task 1.2 - Analysis of Overtopping and Coastal Flooding | Technical Memorandum | 2020-02-28 | 2020-03-30 | 10950 | 3650 | 14600
Total Task 1 Cost |  |  |  | 13914 | 4620 | 18534
Task 2: Quantitative Analysis of Coastal Change and Sediment Transport Processes
Sub-task 2.1 Shoreline Change Analysis |  |  |  | 8424 | 3140 | 11564
Sub-task 2.2 - Lonshore Sediment Transport Model |  |  |  | 22200 | 7400 | 29600
Sub-task 2.2 - Hydrodynamic and Storm Surge Model | Technical Memorandum | 2020-03-15 | 2020-04-15 | 18195 | 6065 | 24260
Total Task 2 Cost |  |  |  | 48819 | 16605 | 65424
Task 3: Initial Engineering Analysis to Screen Potential Alternatives
Sub-task 3.1 - Alternatives Analysis |  |  |  | 8220 | 2740 | 10960
Sub-task 3.2 - Screening of Alternatives | Technical Memorandum | 2020-04-30 | 2020-05-31 | 4680 | 1560 | 6240
Total Task 3 Cost |  |  |  | 12900 | 4300 | 17200
Task 4: Prioritize Shore and Flood Protection Strategies
Sub-task 4.1 - Working Session #1 | Powerpoint Presentation | 2020-04-30 | 2020-05-31 | 7329 | 2425 | 9754
Sub-task 4.2 - Prioritize Shore and Flood Protection |  |  |  | 16230 | 5410 | 21640
Sub-task 4.3 - Working Session #2 | Powerpoint Presentation | 2020-05-31 | 2020-06-30 | 7329 | 2425 | 9754
Sub-task 4.4 - Draft Report | Draft Report | 2020-06-01 | 2020-06-30 | 16710 | 5570 | 22280
Sub-task 4.5 - Final Report | Final Report | 2020-06-30 | 2020-06-30 | 6720 | 2240 | 8960
Total Task 4 Cost |  |  |  | 54318 | 18070 | 72388
TOTAL PROJECT COST |  |  |  | 129951 | 43595 | 173546

## BUDGET
FY20 Coastal Resilience Grant - Evaluation of Coastal Processes and Storm Impacts to Support Resilient Planning and Mitigation Strategies for the Vineyard Haven Harbor Shoreline
| GRANT | [11 empty] | Total Task (Grant) | IN-KIND / CASH MATCH | [11 empty] | Total Task (Match) | Total Project Cost
| Project Team Hours | [7 empty] | Direct Costs |  |  |  |  | Project Team Hours | [7 empty] | Direct Costs
| Principal Engineer |  | Senior Engineer |  | GIS Specialist |  | Coastal Engr/Scientist |  | Unit | Quanity | Unit Cost | Total |  | Principal Engineer |  | Senior Engineer |  | GIS Specialist |  | Coastal Engr/Scientist |  | Unit | Quanity | Unit Cost | Total
Hourly Rate | 265 |  | 185 |  | 115 |  | 110 |  | X | X | X | X |  | 265 |  | 185 |  | 115 |  | 110 |  | X | X | X | X
Task 1: Site -Specific Analysis of Overtopping and Coastal Flooding | Hours | Total | Hours | Total | Hours | Total | Hours | Total | [5 empty] | Hours | Total | Hours | Total | Hours | Total | Hours | Total
Sub-task 1.1 - Kick-Off Meeting | 6 | 1590 | 0 | 0 | 0 | 0 | 12 | 1320 | Travel | 1 | 54 | 54 | 2964 | 2 | 530 | 0 | 0 | 0 | 0 | 4 | 440 |  |  |  | 0 | 970 | 3934
Sub-task 1.2 - Analysis of Overtopping and Coastal Flooding | 6 | 1590 | 18 | 3330 | 18 | 2070 | 36 | 3960 |  |  |  | 0 | 10950 | 2 | 530 | 6 | 1110 | 6 | 690 | 12 | 1320 |  |  |  | 0 | 3650 | 14600
Total Task 1 Cost | [12 empty] | 13914 | [12 empty] | 4620 | 18534
Task 2: Quantitative Analysis of Coastal Change and Sediment Transport Processes
Sub-task 2.1 Shoreline Change Analysis | 3 | 795 | 15 | 2775 | 36 | 4140 | 6 | 660 | Travel | 1 | 54 | 54 | 8424 | 1 | 265 | 5 | 925 | 12 | 1380 | 2 | 220 | RTK | 1 | 350 | 350 | 3140 | 11564
Sub-task 2.2 - Lonshore Sediment Transport Model | 15 | 3975 | 45 | 8325 | 0 | 0 | 90 | 9900 |  |  |  | 0 | 22200 | 5 | 1325 | 15 | 2775 | 0 | 0 | 30 | 3300 |  |  |  | 0 | 7400 | 29600
Sub-task 2.2 - Hydrodynamic and Storm Surge Model | 15 | 3975 | 30 | 5550 | 18 | 2070 | 60 | 6600 |  |  |  | 0 | 18195 | 5 | 1325 | 10 | 1850 | 6 | 690 | 20 | 2200 |  |  |  | 0 | 6065 | 24260
Total Task 2 Cost | [12 empty] | 48819 | [12 empty] | 16605 | 65424
Task 3: Initial Engineering Analysis to Screen Potential Alternatives
Sub-task 3.1 - Alternatives Analysis | 6 | 1590 | 18 | 3330 | 0 | 0 | 30 | 3300 |  |  |  | 0 | 8220 | 2 | 530 | 6 | 1110 | 0 | 0 | 10 | 1100 |  |  |  | 0 | 2740 | 10960
Sub-task 3.2 - Screening of Alternatives | 6 | 1590 | 6 | 1110 | 0 | 0 | 18 | 1980 |  |  |  | 0 | 4680 | 2 | 530 | 2 | 370 | 0 | 0 | 6 | 660 |  |  |  | 0 | 1560 | 6240
Total Task 3 Cost | [12 empty] | 12900 | [12 empty] | 4300 | 17200
Task 4: Prioritize Shore and Flood Protection Strategies
Sub-task 4.1 - Working Session #1 | 9 | 2385 | 12 | 2220 | 6 | 690 | 18 | 1980 | Travel | 1 | 54 | 54 | 7329 | 3 | 795 | 4 | 740 | 2 | 230 | 6 | 660 |  |  |  | 0 | 2425 | 9754
Sub-task 4.2 - Prioritize Shore and Flood Protection | 18 | 4770 | 24 | 4440 | 18 | 2070 | 45 | 4950 |  |  |  | 0 | 16230 | 6 | 1590 | 8 | 1480 | 6 | 690 | 15 | 1650 |  |  |  | 0 | 5410 | 21640
Sub-task 4.3 - Working Session #2 | 9 | 2385 | 12 | 2220 | 6 | 690 | 18 | 1980 | Travel | 1 | 54 | 54 | 7329 | 3 | 795 | 4 | 740 | 2 | 230 | 6 | 660 |  |  |  | 0 | 2425 | 9754
Sub-task 4.4 - Draft Report | 12 | 3180 | 30 | 5550 | 12 | 1380 | 60 | 6600 |  |  |  | 0 | 16710 | 4 | 1060 | 10 | 1850 | 4 | 460 | 20 | 2200 |  |  |  | 0 | 5570 | 22280
Sub-task 4.5 - Final Report | 9 | 2385 | 9 | 1665 | 6 | 690 | 18 | 1980 |  |  |  | 0 | 6720 | 3 | 795 | 3 | 555 | 2 | 230 | 6 | 660 |  |  |  | 0 | 2240 | 8960
Total Task 4 Cost | [12 empty] | 54318 | [12 empty] | 18070 | 72388
TOTAL PROJECT COST | [12 empty] | 129951 | [12 empty] | 43595 | 173546
[26 empty] | 25.12% | (Note: Match must be at least 25% of total project cost)