**Beach Road Weekend Music Festival**

**Exhibit A**

Details of the License:

**Location:**

1. Tisbury, MA

**Event Date:**

1. July 23 -25, 2021

**Event Times:**

1. July 23 6-9 pm; Doors at 4 pm
2. July 24 6-9 pm; Doors at 4 pm
3. July 25 6-9 pm; Doors at 4 pm

**Event Setup:**

1. July 20-22, 2021

Event Strike

1. July 26-27, 2021 9pm

**Site:**

1. Veterans Memorial Park;
	1. Ballfields will be available for use by the Town through July 19, 2021
2. parking lot adjacent to Park; and access road to parking lot;

**Beach Road Weekend Music Festival**

**Exhibit B**

**Load in, Performances, and Load Out schedule**

**July 20 – 22 2021**

* Power & Generator installation
* Plywood “Road” installation for stage trucking to be driven on field
* Stage arrival and installation
* Removal of plywood “road”
* Food and merchant tent installation
* Fencing installation thru outfield of ballfields
* Sound and Light mix position installed
* Installation of field flooring for seating area
* Food and merchant load in
* Finalizing of staging plans and projection screen installation
* Load in of projection gear
* Sound and projection equipment checks

**Friday July 23, 2021 through Sunday July 25, 2021**

Musical Performances

**Monday July 26, 2021 through Tuesday July 27, 2021**

Load out and site breakdown, plus cleanup

Access to ballfield restored by 9pm Tuesday evening.